## Sheet1
Defect identifier | def_nop_fname_001 | def_nop_lname_002 | def_nop_social_media_003 | def_nop_digi_download_atc_004 | def_nop_digi_download_wishlist_005
Defect summary | Expected result = User should not be register with numbers only in first name Actual result = User is able to register with numbers only in first name | Expected result = User should not be register with numbers only in last name Actual result = User is able to register with numbers only in last name | Expected result = All social media icons redirection shoul work Actual result = One icon is not working | Expected result = All items add to cart button should add item into cart Actual result = The items which don’t have any price when clicked on add to cart button then its details page is opening | Expected result = All items wishlist button should add item into wishlist Actual result = The items which don’t have any price when clicked on wishlist button then its details page is opening
Test Id | TC‑006_invalid_fname | TC‑007_invalid_lname | TC‑006_social_media | TC‑006_dd_atc | TC‑007_dd_wishlist
Test case name | TC_nop_reg_invalid_fname_numbers | TC_nop_reg_invalid_lname_numbers | TC_nop_social_media_icons | TC_nop_digital_downloads_add_to_cart | TC_nop_digital_downloads_wishlist
Module name | Register Page | Register Page | Home Page | Digital Downloads Tab | Digital Downloads Tab
severity | Medium | Medium | Low | Medium | Medium
priority | High | High | medium | Medium | Medium
Raised by | Prathamesh Sangale (Tester name) | Prathamesh Sangale (Tester name) | Prathamesh Sangale (Tester name) | Prathamesh Sangale (Tester name) | Prathamesh Sangale (Tester name)
Assigned to | Vaishali Sonanis (TL name). | Vaishali Sonanis (TL name) | Vaishali Sonanis (TL name) | Vaishali Sonanis (TL name) | Vaishali Sonanis (TL name)
Date of assignment | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05
status | open | open | open | open | open
Snap shots
Fixed by | firstName lastName(Developer name) | firstName lastName(Developer name) | firstName lastName(Developer name) | firstName lastName(Developer name) | firstName lastName(Developer name)
Date of fixing=
Approvals=manager name | firstName LastName(Manager name) | firstName LastName(Manager name) | firstName LastName(Manager name) | firstName LastName(Manager name) | firstName LastName(Manager name)