## Sheet1
Sr. No | Module Name | Test Items | Features to be Tested | Features not to be Tested | Approach | Pass/Fail Criteria | Environment | Responsibility | Schedule | Risk/Contingency | Approval
1 | Home Page | Social media icons redirections, Footer links, nopCommerce link, News link, Details button, Newsletter textbox, SUBSCRIBE button, Community poll radio buttons, Vote button, View News Archieve link, Currency dropdown, searchbox | Social media icons redirections, Footer links, nopCommerce link, News link, Details button, Newsletter textbox, SUBSCRIBE button, View News Archieve link | Vote button, Community poll radio buttons | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if all functions work as per SRS | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis
2 | Register | Gender radio buttons, First name field, Last name field, Email field, Company name field, Password field, Confirm Password field, Register button, Newsletter checkbox | Gender radio buttons, First name field, Last name field, Email field, Company name field, Password field, Confirm Password field, Register button | Newsletter checkbox | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if all functions work as per SRS | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis
3 | Login | Email field, Password field, Remember me checkbox, Forgot password link, LOG IN Button, REGISTER button | Email field, Password field, Remember me checkbox, LOG IN Button, REGISTER button | Forget password link | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if after entering valid credentials user gets logged in | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis
4 | Wishlist | Add to cart checkbox, Edit link, Qty box, Remove button, UPDATE WISHLIST button, ADD TO CART button, Email a friend button, Searchbox | Add to cart checkbox, Edit link, Qty box, Remove button, UPDATE WISHLIST button, ADD TO CART button | Email a friend button | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if product gets add to wishlist | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis
5 | Shopping cart | Arraow keys, Qty box, Remove button, Edit link, Continue Shopping button, Estimate Shipping button, Gift wrapping dropdown, Discount code field, APPLY COUPON button, Gift Cards field, ADD GIFT CARD button, I agree checkbox, CHECKOUT button | Arraow keys, Qty bax, Remove button, Edit link, Continue Shopping button, Estimate Shipping button, Gift wrapping dropdown, Discount code field, APPLY COUPON button, I agree checkbox, CHECKOUT button | Gift Cards field, ADD GIFT CARD button | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if product gets added to cart | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis
6 | Computers tab | product category redirection | product category redirection |  | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if all functinalties work as expected | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis
7 | Electronics tab | product category redirection | product category redirection |  | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if all functinalties work as expected | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis
8 | Apparel tab | product category redirection | product category redirection |  | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if all functinalties work as expected | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis
9 | Digital download tab | Sort by filter, display filter, product category redirection, grid view, list view, add to cart button, compare button, wishlist button | Sort by filter, display filter, product category redirection, grid view, list view, add to cart button, wishlist button | compare button | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if all functinalties work as expected | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis
10 | Books tab | Sort by filter, display filter, product category redirection, grid view, list view, add to cart button, compare button, wishlist button, Filter by price filter | Sort by filter, display filter, product category redirection, grid view, list view, add to cart button, wishlist button, Filter by price filter | compare button | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if all functinalties work as expected | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis
11 | Jewelry tab | Sort by filter, display filter, product category redirection, grid view, list view, add to cart button, compare button, wishlist button, Filter by price filter | Sort by filter, display filter, product category redirection, grid view, list view, add to cart button, wishlist button, Filter by price filter | compare button | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if all functinalties work as expected | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis
12 | Gift Card tab | Sort by filter, display filter, product category redirection, grid view, list view, add to cart button, compare button, wishlist button, Filter by price filter | Sort by filter, display filter, product category redirection, grid view, list view, add to cart button, wishlist button, Filter by price filter | compare button | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if all functinalties work as expected | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis
13 | Links | Home link, Categories links, Manufacturer links, view all link, recently viewed products link, popular tags link, popular tag view all link | Categories links, Manufacturer links, view all link, popular tags link, popular tag view all link | recently viewed products link | Automation/Manual Selenium WebDriver, TestNG, Cucumber | Pass if all functinalties work as expected | Windows 10/11, MacOS, Linux, Android/iOS, Browsers (Chrome, Firefox, Edge, Brave) | Prathamesh Sangale | 2025-08-28 | No risk | Vaishali Sonanis